## Sheet1
BÀI TẬP CAPSTONE BOOTSTRAP
Deadline: 01/05/2024
LỚP BC68_GROUP 07:
- BÙI HỮU CÔNG | devCong
- LÊ MINH KHOA | devKhoa
TRANG MẪU: ĐỀ sỐ 6
https://wp.w3layouts.com/farmstead/
THÔNG TIN KẾT QUẢ:
- Link github source code: | https://github.com/congkti/bc68g7-bscapstone
- Link deploy web: | https://bc68g7-bscapstone.vercel.app/
- Link Youtube: | https://youtu.be/fI8MpFVwrJ8
- Link source code GG drive | https://drive.google.com/drive/folders/1TF5vcWAy_NN1FfpXb5y3hZD5Kfr1DCTL?usp=sharing
CHIA CÔNG VIỆC
Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Setup dự án + file ban đầu | 2024-04-16 | 2024-04-17 | 100% | devCong
Header + Page head (Title + Breadcrumb nav) | 2024-04-18 | 2024-04-20 | 100% | devCong |  | 2024-04-20 | 100% | devCong
Footer + Testimonial + go to top | 2024-04-18 | 2024-04-20 | 100% | devKhoa |  | 2024-04-20 | 100% | devKhoa
Merge code phần dùng chung Header+Footer+... để tạo base template làm các trang sau | 2024-04-20 | 2024-04-21 | 100% | devCong | 2024-04-21 | 2024-04-22 | 100% | devCong
Làm trang Home page | 2024-04-22 | 2024-04-24 | 100% | devCong |  | 2024-04-24 | 100% | devCong
Làm trang About | 2024-04-25 | 2024-04-27 | 95% | devCong | 2024-04-27 | 2024-04-28 | 100% | devCong
Làm trang Contact |  |  | 95% | devCong | 2024-04-27 | 2024-04-28 | 100% | devCong
Làm trang Services | 2024-04-22 | 2024-04-29 |  | devKhoa |  |  | 100% | devKhoa
Làm trang Blog post |  |  |  | devKhoa |  |  | 100% | devKhoa
Làm trang Blog Detail |  |  |  | devKhoa |  |  | 100% | devKhoa
Làm trang 404 |  |  |  | devKhoa |  |  | 100% | devKhoa
Merge code + Chỉnh sửa + Final version | 2024-04-29 | 2024-04-30 |  | devCong |  | 2024-04-30 | 100% | devCong